EXECUTION PLAN

Home Services AI Automation Agency

Zeem AI Repurpose → $10K MRR in 90 Days

CONFIDENTIAL — Internal Use Only

Issued: May 2, 2026

# Mission Lock

Target: $10,000 Monthly Recurring Revenue from HVAC and plumbing companies in Dallas-Fort Worth, using a repurposed Zeem AI platform.

Product: AI-powered missed-call recovery, lead qualification, and appointment booking delivered as a managed service.

Price Point: $2,000–$4,000 setup + $1,500–$3,000/month retainer per client.

Clients Needed: 4–7 paying clients at target MRR.

NON-NEGOTIABLE RULE: Every task you do must connect to one of three outcomes: (1) more outbound touches sent, (2) a prospect on a discovery call, or (3) a pilot going live. If a task does not serve one of these three, stop and ask before doing it.

# Deliverable 1: Outreach Infrastructure Setup

Deadline: Complete within 48 hours of receiving this plan.

## 1A. Cold Email Domain and Warmup

You need a separate domain for cold outreach to protect your main brand domain from spam reputation damage.

Step-by-step:

- Go to Namecheap or GoDaddy. Buy a domain similar to your brand but not identical. Examples: getzeem.io, zeemhq.com, zeemautomation.com. Cost: $10–$15/year.

- Point the domain's DNS to Google Workspace or Zoho Mail. Create 3 email accounts: yourname@newdomain.com, hello@newdomain.com, outreach@newdomain.com. Cost: $6–$12/mo per mailbox on Google Workspace, or free tier on Zoho.

- Set up SPF, DKIM, and DMARC records for the new domain. This is mandatory for deliverability. Each email provider gives you the exact DNS records to add. Google: Admin Console > Apps > Google Workspace > Gmail > Authenticate Email. Zoho: Mail Admin > Domain Settings > Email Authentication.

- Sign up for Instantly.ai ($30/mo Starter plan). Connect all 3 mailboxes. Enable the warmup feature on each mailbox. Set warmup to: 2 emails/day for days 1–7, then ramp to 5/day for days 8–14. Do not send any cold emails until day 14.

- Verify DNS propagation using mail-tester.com. Send a test email from each mailbox to the address mail-tester gives you. Target score: 9/10 or higher.

| KPI | Benchmark | How to Verify |
| --- | --- | --- |
| Domain purchased | Within 24 hours | Screenshot of domain registrar |
| 3 mailboxes created | Within 24 hours | Screenshot of inbox logins |
| SPF/DKIM/DMARC live | Within 36 hours | mail-tester.com score 9+/10 |
| Instantly warmup active | Within 48 hours | Screenshot of Instantly dashboard showing warmup status |
| Mail-tester score | 9/10 or higher | Screenshot of test results |

## 1B. LinkedIn Profile Optimization

Your LinkedIn profile is your second outreach channel and the primary trust signal when prospects Google you.

- Headline: Change to: "I help HVAC & plumbing companies stop losing jobs to missed calls | AI-powered lead recovery"

- About Section: Write 3–4 sentences. Problem (contractors lose $5K–$50K/mo to missed calls), solution (AI answers and qualifies 24/7), proof (mention speed: under 30 seconds response time), CTA ("DM me 'demo' to see it work on your number").

- Banner image: Use Canva. Simple text on dark background: "Your phones ring. We make sure you never miss a job." Include your brand name.

- Featured section: Add a Loom link (you will create this in Deliverable 3).

| KPI | Benchmark |
| --- | --- |
| Headline updated | Within 24 hours |
| About section rewritten | Within 24 hours |
| Banner image uploaded | Within 48 hours |

# Deliverable 2: Target Account List (300 Accounts)

Deadline: 100 accounts within 48 hours. 300 accounts within 7 days.

## 2A. Ideal Customer Profile (ICP)

Every account on your list must match ALL of these criteria:

| Filter | Requirement | Why |
| --- | --- | --- |
| Industry | HVAC, plumbing, electrical, roofing, or garage door | Highest call volume, highest job values, owner-operated |
| Location | Dallas-Fort Worth metro area | Sun Belt growth, high density, owner-operator culture |
| Company size | 2–50 employees | Big enough to have real revenue, small enough that owner decides |
| Online presence | Has a Google Business profile with 10+ reviews | Signals active business that invests in marketing |
| Phone behavior | Has a listed phone number on website/Google | Proves phone is a revenue channel for them |

## 2B. How to Build the List

Method 1: Google Maps manual scraping (free, do this first)

- Open Google Maps. Search: "HVAC company Dallas Fort Worth"

- For each result that matches ICP: copy business name, phone number, website URL, Google rating, review count into a Google Sheet.

- Repeat for: "plumbing company Dallas", "plumbing company Fort Worth", "HVAC repair Arlington TX", "plumber Plano TX", "HVAC company Frisco TX". Cover the full metro.

- Visit each website. Find the owner/manager name (usually on About page). Find their email (usually on Contact page or footer). Add to your sheet.

- If no email visible on website: check LinkedIn for the owner. Note their LinkedIn URL in your sheet.

Method 2: Apollo.io (free tier, 50 credits/mo)

- Sign up at Apollo.io. Use filters: Industry = Construction/HVAC/Plumbing, Location = Dallas-Fort Worth TX, Company size = 1–50, Title = Owner OR President OR General Manager.

- Export results. Cross-reference with your Google Maps list to fill in missing emails.

Method 3: Use Zeem AI's existing outreach engine

- Your platform already has Google Places integration. Modify the search queries from "personal injury lawyer Houston" to "HVAC company Dallas" etc.

- Run the website scraper against discovered businesses to extract emails.

- Export to your master spreadsheet.

Spreadsheet columns (mandatory):

| Column | Example | Required? |
| --- | --- | --- |
| Company Name | ABC Plumbing LLC | Yes |
| Owner/Manager Name | Mike Johnson | Yes |
| Phone | (214) 555-0123 | Yes |
| Email | mike@abcplumbing.com | Yes (or LinkedIn) |
| Website | abcplumbing.com | Yes |
| Google Rating | 4.6 | Yes |
| Review Count | 187 | Yes |
| City | Plano, TX | Yes |
| Service Type | HVAC | Yes |
| LinkedIn URL | linkedin.com/in/mikejohnson | If no email |
| Outreach Status | Not contacted | Yes |
| Notes | Missed call when I tested | Optional |

| KPI | Benchmark | How to Verify |
| --- | --- | --- |
| Accounts loaded (batch 1) | 100 within 48 hours | Share Google Sheet link |
| Accounts loaded (full) | 300 within 7 days | Share Google Sheet link |
| Email found rate | 60%+ of accounts have a direct email | Column count in sheet |
| ICP match rate | 100% of accounts match all ICP filters | Spot check 20 random rows |

# Deliverable 3: Repurpose Zeem AI for Home Services

Deadline: Working demo within 7 days.

You already have a production-grade intake platform. Here is exactly what to change and what to leave alone.

## 3A. What Stays the Same (Do Not Touch)

- Twilio SMS webhook infrastructure (/api/webhook/sms)

- New Lead webhook (/api/webhook/new-lead)

- OpenAI tool-calling booking mechanism

- Regex fallback booking detection

- Stop-word detection and TCPA compliance

- Conversation and message storage schema

- Stripe billing integration

- Dashboard: conversations, bookings, client management views

- Delayed response simulation (2–5 second human typing delay)

## 3B. What Changes: Prompt Layer

File to modify: src/prompts/legal-intake.js (rename to src/prompts/home-services-intake.js)

Current structure (legal):

- Personal Injury prompt → asks about injuries, statute of limitations, existing representation

- Family Law prompt → asks about marriage, children, urgency

- Criminal Defense prompt → asks about charges, court dates, bail

New structure (home services):

HVAC Service Prompt — System instructions:

"You are a friendly, professional AI assistant for [COMPANY_NAME], an HVAC company in [CITY]. Your job is to qualify the lead and book a service appointment. You must:

- Greet warmly and acknowledge their inquiry within the first message

- Ask what HVAC issue they are experiencing (AC not cooling, heater not working, strange noises, annual maintenance, new install)

- Ask about urgency: Is this an emergency (no heat in winter, no AC in summer) or can it be scheduled?

- Ask for the service address (city/zip at minimum)

- Ask if they are the homeowner or tenant

- If qualified, offer available appointment slots using the book_appointment tool

- Never quote prices. Say: 'Our technician will provide an on-site estimate at no charge during the service call.'

- Never diagnose the problem. Say: 'That sounds like something our techs see regularly. Let us get someone out to take a look.'

- If they mention a competitor quote, say: 'We are happy to give you a second opinion. No obligation.'"

Plumbing Service Prompt — System instructions:

"You are a friendly, professional AI assistant for [COMPANY_NAME], a plumbing company in [CITY]. Your job is to qualify the lead and book a service appointment. You must:

- Greet warmly and acknowledge their inquiry

- Ask what plumbing issue they are experiencing (leak, clogged drain, water heater, sewer line, fixture install, emergency burst pipe)

- Ask about urgency: Is there active water damage or flooding right now?

- If emergency: escalate immediately. Say: 'Let me get our emergency dispatcher on this right now. Can you confirm your address?'

- Ask for the service address

- Ask if they are the homeowner or tenant

- If qualified, offer available appointment slots using the book_appointment tool

- Never quote prices. Say: 'Our plumber will assess the situation on-site and give you a clear quote before any work starts.'

- Never diagnose. Say: 'That is a common issue our team handles. Let us get someone out to you.'"

Electrical / Roofing / Garage Door prompts:

Follow the same pattern. Adjust the service-specific questions (e.g., for electrical: "Is the issue with a specific outlet, your panel, or whole-house?"; for roofing: "Is there active leaking? When was your last roof inspection?"). You can build these after the first two are working.

## 3C. What Changes: Data Model

File to modify: src/config/schema.sql and the clients table logic

| Current Field (Legal) | New Field (Home Services) | Notes |
| --- | --- | --- |
| practice_area | service_type | Values: hvac, plumbing, electrical, roofing, garage_door |
| qualification_criteria (legal-specific) | qualification_criteria (home-services) | New fields: issue_type, urgency_level, is_homeowner, service_address |
| No change needed | conversations table | Schema is niche-agnostic |
| No change needed | bookings table | Schema is niche-agnostic |
| No change needed | messages table | Schema is niche-agnostic |

## 3D. What Changes: Outreach Engine

File to modify: src/services/outreach.js

- Google Places queries: Change from "personal injury lawyer Houston" to "HVAC company Dallas", "plumber Fort Worth", "plumbing company Arlington TX", etc.

- Email template: Replace legal-specific copy with home services copy. See the cold email template in Deliverable 4 below.

- Prospect enrichment: The website scraper already looks for /contact and /about pages. No changes needed. It will work on contractor websites the same way.

## 3E. What Changes: Landing Page and Brand

- Replace all "law firm" / "attorney" / "legal" language with "contractor" / "home services" / "HVAC & plumbing"

- Hero headline: "Never miss a service call again. AI answers your phone 24/7."

- Subheadline: "HVAC and plumbing companies using [Brand] recover $5K–$50K/month in missed revenue."

- Keep the free 14-day pilot offer. This is your wedge.

- Add a "Call Our Demo Line" button with a live Twilio number running the HVAC prompt so prospects can test it themselves.

| KPI | Benchmark | How to Verify |
| --- | --- | --- |
| HVAC prompt written and tested | Day 3 | Send 10 test conversations in the AI simulator |
| Plumbing prompt written and tested | Day 4 | Send 10 test conversations in the AI simulator |
| Landing page updated | Day 5 | URL live and loading correctly |
| Demo Twilio number live | Day 6 | Call the number, interact with the AI, verify booking works |
| Outreach queries updated | Day 6 | Run discovery on 'HVAC company Dallas', verify results |
| Full end-to-end test | Day 7 | New lead webhook > AI SMS > qualification > booking > dashboard |

# Deliverable 4: Outreach Sequences and Sales Materials

Deadline: Ready to send by day 14 (when email warmup completes).

## 4A. Cold Email Sequence

Email 1 — Initial (Day 0)

Subject: quick idea to recover lost calls at {{company}}

Hi {{first_name}},

I looked at {{company}} and noticed something most HVAC/plumbing companies in DFW deal with: when your techs are on a job and the phone rings, that call often goes to voicemail. That caller usually calls the next company on Google.

We built a system that answers those calls in under 30 seconds, qualifies the lead, and books the appointment directly into your calendar — 24/7, no extra staff.

If useful, I can send a 2-minute video showing exactly how this would work for {{company}}.

Worth a look?

— {{your_name}}

Email 2 — Follow-up (Day 3)

Subject: Re: quick idea to recover lost calls at {{company}}

Hi {{first_name}},

Quick follow-up. Most contractors we talk to are losing 20–40% of inbound calls to voicemail during business hours alone. After hours, it is close to 100%.

At an average job value of $500–$2,000, that is $5K–$20K/month in revenue walking out the door.

Happy to show you a live demo. Takes 5 minutes. You can even call our AI line yourself and see how it handles a real service request.

— {{your_name}}

Email 3 — Social proof (Day 7)

Subject: how DFW contractors are handling missed calls

Hi {{first_name}},

Wanted to share something quick: we ran a test for a plumbing company in [city] and their missed-call rate dropped from 35% to under 2% in the first week. The system booked 12 appointments they would have lost.

No new staff, no call center, no answering service contract. Just an AI that picks up, qualifies, and books.

Want me to build a free demo using your actual business info so you can see what this looks like for {{company}}?

— {{your_name}}

Email 4 — Breakup (Day 14)

Subject: closing the loop

Hi {{first_name}},

I will not keep emailing. If recovering missed calls is not a priority right now, totally understand.

If it ever becomes one, the offer stands — free 14-day pilot, no contracts, cancel anytime.

Wishing {{company}} a strong season.

— {{your_name}}

## 4B. LinkedIn Sequence

- Connection request (Day 0): "Hey {{first_name}}, saw you run {{company}} in DFW. I work with HVAC/plumbing companies on reducing missed calls — thought it would be good to connect."

- First message (Day 2): "Quick question — when your techs are out on jobs, what happens to incoming calls? Most companies I talk to are losing 20–40% to voicemail. We built something that fixes that. Want me to send a 2-min video?"

- Value message (Day 5): Send a Loom video (60–90 seconds) showing the AI answering a test call, qualifying a lead, and booking an appointment. Personalize it by saying the prospect's company name in the video."

- Binary close (Day 9): "Is missed-call recovery already solved for you, or still manual?"

## 4C. Loom Teardown Videos (3 required)

These are your most powerful sales assets. Each video should be 60–90 seconds maximum.

Video 1: "The Missed Call Problem"

- Call a real HVAC company during business hours. If it goes to voicemail or rings forever, record it.

- Then call your demo AI line. Show it answering in under 30 seconds, qualifying the lead, and booking.

- Narrate the cost: "That missed call at a $1,500 average job value just cost them $1,500."

Video 2: "Live Demo Walkthrough"

- Screen-share the dashboard. Show a conversation where the AI qualified and booked a lead.

- Show the booking appearing in the calendar.

- Show the conversation transcript so they can see the AI sounds natural and professional.

Video 3: "ROI Calculator"

- Walk through simple math on screen: "If you get 200 calls/month and miss 30%, that is 60 missed calls. At a 25% close rate and $1,200 average job, that is $18,000/month in lost revenue. Our system costs $2,500/month. That is a 7x return."

| KPI | Benchmark |
| --- | --- |
| Email sequence loaded in Instantly | Day 12 |
| LinkedIn sequence drafted | Day 10 |
| 3 Loom videos recorded and hosted | Day 10 |
| First cold email batch sent | Day 15 (after warmup) |
| First LinkedIn connection batch sent | Day 8 |

# Deliverable 5: Sales Process and Pilot Framework

Deadline: Have all materials ready by day 10.

## 5A. Discovery Call Script

Every discovery call follows this structure. Do not freestyle.

- Open (2 min): "Thanks for taking the time, {{first_name}}. I know you are busy so I will keep this tight. Quick question before anything else — how do you currently handle calls when your team is out on jobs?"

- Diagnose (5 min): Listen. Ask: How many calls/month? What happens to after-hours calls? Do you use an answering service? What is your average job value? How many techs on the road at once?

- Live demo (3 min): "I am going to call your business number right now so we can see what happens." Call their number on speakerphone. If it goes to voicemail or takes more than 3 rings: "That right there is what we fix. Let me show you what it looks like when our system is running." Then call your demo line and let them hear the AI in action.

- ROI frame (2 min): "Based on what you told me — {{X}} calls/month, {{Y}}% missed, ${{Z}} average job — you are leaving roughly ${{calculated}} on the table every month. Our system costs ${{price}}/month. Even if we only capture half those lost calls, that is a {{multiplier}}x return."

- Close (1 min): "Here is what I would suggest: we run a free 14-day pilot on your actual number. No contracts, no risk. If it works, we keep going. If not, we part friends. Can we get that set up this week?"

## 5B. Pilot Contract Terms

| Term | Detail |
| --- | --- |
| Duration | 14 days, starting from go-live date |
| Cost | Free (no setup fee, no retainer during pilot) |
| What they provide | Access to forward their phone line to Twilio number, business hours, service types, average job values |
| What you provide | AI intake system configured for their business, 24/7 call handling, daily email report of conversations and bookings |
| Success criteria | Defined upfront: e.g., 'If the system books 5+ appointments in 14 days, we continue at $2,500/mo' |
| Conversion terms | After pilot: $2,000–$4,000 setup fee + $1,500–$3,000/month. Month-to-month. 30-day cancellation notice. |

## 5C. Onboarding Checklist (When Pilot is Sold)

- Collect: business name, service types offered, service area (zip codes), business hours, owner/manager name and cell phone for escalations

- Collect: average job value by service type, current call volume estimate, current CRM (if any)

- Set up: new Twilio number with local DFW area code (214 or 972)

- Configure: AI prompt with their specific business info, service types, and qualification criteria

- Test: run 10 simulated conversations through the AI simulator in the dashboard

- Set up: call forwarding from their existing business number to the Twilio number

- Go live: monitor first 24 hours closely. Review every conversation. Tune the prompt if needed.

- Day 3 check-in: call the client. Share transcript highlights. Ask for feedback.

- Day 7 check-in: send ROI report (calls handled, appointments booked, estimated revenue recovered)

- Day 14: pilot review call. Present full ROI report. Close on paid retainer.

# Weekly Execution Cadence

Once outreach is live, this is your weekly operating rhythm. Do not deviate.

| Day | Focus | Output |
| --- | --- | --- |
| Monday | Load 50 new accounts + send 30 cold emails | Updated spreadsheet + Instantly send log |
| Tuesday | Send 20 LinkedIn connections + 10 follow-up emails | LinkedIn activity log |
| Wednesday | Discovery calls (book all calls Tue–Thu) | Call notes in spreadsheet |
| Thursday | Discovery calls + send 30 cold emails | Call notes + Instantly send log |
| Friday | Follow-up all open conversations + pilot check-ins | Updated pipeline status |
| Saturday | Record 1 new Loom video or write 1 LinkedIn post | Content published or queued |
| Sunday | Off or light account research | No output required |

# Master Timeline: 90 Days to $10K MRR

## Days 1–14: Foundation

| Task | Deadline | KPI |
| --- | --- | --- |
| Buy outreach domain, create mailboxes, start warmup | Day 1–2 | Domain live, warmup active |
| Optimize LinkedIn profile | Day 1–2 | Headline and About updated |
| Build 100 target accounts | Day 1–3 | 100 rows in spreadsheet |
| Rewrite Zeem AI prompts for HVAC + plumbing | Day 3–5 | 10 test convos per prompt pass QA |
| Update landing page copy | Day 5–6 | Live URL |
| Set up demo Twilio line | Day 5–6 | Callable and booking correctly |
| Record 3 Loom videos | Day 7–10 | Hosted links |
| Draft and load email sequences in Instantly | Day 10–12 | Sequences loaded |
| Send first LinkedIn connection batch | Day 8 | 25 connections sent |
| Build to 300 accounts | Day 3–14 | 300 rows in spreadsheet |
| Send first cold email batch | Day 15 | 30 emails sent |

## Days 15–30: Pipeline Building

| KPI | Target |
| --- | --- |
| Outbound emails sent per week | 120–150 |
| LinkedIn connections sent per week | 50–75 |
| Replies received (cumulative) | 20+ |
| Discovery calls booked (cumulative) | 8+ |
| Paid audits or free pilots started | 3+ |
| Pipeline value | $15K–$30K in potential MRR |

## Days 31–60: Pilot Conversion

| KPI | Target |
| --- | --- |
| Pilots running simultaneously | 2–3 |
| First documented ROI result | At least 1 pilot with provable appointments booked |
| Pilot-to-paid conversion rate | 50%+ |
| Paying clients | 2–3 |
| MRR | $3K–$9K |
| First case study published | Yes |
| Partner referral sources identified | 2+ (e.g., CRM consultants, marketing agencies) |

## Days 61–90: Scale and Standardize

| KPI | Target |
| --- | --- |
| Paying clients | 4–7 |
| MRR | $8K–$20K |
| Client churn | 0 |
| Median onboarding time | Under 7 days |
| Expansion sales (upsell existing clients) | 1+ |
| Case studies published | 2 |
| Second metro prospecting started | Only after DFW produces meetings without heroic effort |

# The DO NOT List

If you catch yourself doing any of these, stop immediately and get back to the deliverables above.

- Do NOT build new features into the platform before you have 3 paying clients

- Do NOT start a second niche before home services is producing $5K+ MRR

- Do NOT target a second city before DFW is producing meetings consistently

- Do NOT redesign the dashboard, add analytics, or refactor code

- Do NOT spend more than 1 hour/day on content creation (LinkedIn posts, videos)

- Do NOT attend networking events, conferences, or webinars as a substitute for outbound

- Do NOT build a website beyond the single landing page

- Do NOT hire anyone before $10K MRR

- Do NOT switch tech stacks, add new AI models, or experiment with agent frameworks

- Do NOT sell to legal firms simultaneously. Park Zeem AI's legal vertical until home services is profitable.

First deliverable due: 48 hours.

Report back with: domain purchased, warmup active, 100 accounts loaded.